## Rollout Summary
Google Home — RPL k=4 re-tier: single-cutover rollout plan
Re-cluster states by RPL into 4 value bands; margin control moves to per-tier tROAS floors (Targets & Floors sheet — margin %s pending leadership sign-off). MEMBERSHIP CUTS OVER ALL AT ONCE on 2026-07-29; TARGETS then step toward their floors gradually (no repeat of the May single-jump tightening). CA/TX/FL standalone, untouched. Generated Jul 28, 2026.
At a glance
Cutover (all membership moves, one event) | 2026-07-29
States re-tiering (readable, ex-standalones) | 35
States changing shells | 20 (57% — a majority-move restructure; phasing is not viable)
Spend in motion | $33,034 (53% of $62,487)
States staying in place | 15 ($29,452, 47%)
Below-gate placements folded in at cutover | 7 (New Hampshire, West Virginia, Wyoming, Delaware, South Dakota, Rhode Island, Hawaii)
Post-cutover freeze | 2 weeks: no target changes, exception screen watch-only, ledger frozen at cutover (--emit-ledger)
Pre-cutover moves (exception track, executed separately) | Pennsylvania & Arizona -> rehab/tightened posture; NM dual-campaign targeting cleanup

## Move Schedule
Move schedule — every state, single cutover 2026-07-29
Grouped by destination tier. 'moving' = physically changes shell at cutover. Below-gate states shown last (thin volume; placed by nearest tier).
new tier | state | current tier | to shell | moving? | spend | conv | RPL | CPC | GP/lead | ROAS
TIER ONE | New Jersey | TIER TWO | T1 shell (existing Tier1RPL80Plus) | yes | 6222 | 73 | 94.4 | 9.74 | 9.6 | 1.11
TIER ONE | Illinois | TIER TWO | T1 shell (existing Tier1RPL80Plus) | yes | 4951 | 64 | 77.4 | 8.45 | 0 | 1
TIER ONE | Minnesota | TIER ONE | T1 shell (existing Tier1RPL80Plus) | — | 1806 | 33 | 81.3 | 8.77 | 26.6 | 1.49
TIER ONE | Massachusetts | TIER THREE | T1 shell (existing Tier1RPL80Plus) | yes | 1343 | 16 | 78.6 | 10.1 | -5.3 | 0.94
TIER ONE | Kansas | TIER TWO | T1 shell (existing Tier1RPL80Plus) | yes | 1031 | 19 | 83.1 | 7.26 | 28.8 | 1.53
TIER ONE | New Mexico | TIER TWO | T1 shell (existing Tier1RPL80Plus) | yes | 656 | 12 | 76.3 | 7.2 | 21.7 | 1.4
TIER ONE | New Hampshire | (below gate) | T1 shell (existing Tier1RPL80Plus) | yes | 368 | 4 | 155.5 | 9.95 | 63.5 | 1.69
TIER ONE subtotal |  |  |  | 6 moving | 16376 | 221 | 85.5 |  | 11.6 | 1.16
TIER TWO | Georgia | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 8721 | 140 | 63.7 | 7.79 | 1.4 | 1.02
TIER TWO | Colorado | TIER THREE | T2 shell (existing Tier2RPL70Plus) | yes | 2810 | 38 | 70.1 | 10.41 | -3.8 | 0.95
TIER TWO | Arizona | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 2648 | 30 | 69.3 | 7.97 | -18.9 | 0.79
TIER TWO | Ohio | TIER ONE | T2 shell (existing Tier2RPL70Plus) | yes | 2599 | 43 | 65.1 | 8.38 | 5.4 | 1.09
TIER TWO | Missouri | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 2436 | 34 | 67.1 | 7.88 | -4.6 | 0.94
TIER TWO | Tennessee | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 2406 | 42 | 64.8 | 7.73 | 7.5 | 1.13
TIER TWO | North Carolina | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 2282 | 53 | 67.3 | 6.73 | 24.3 | 1.56
TIER TWO | Arkansas | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 896 | 22 | 66.5 | 8.22 | 25.8 | 1.63
TIER TWO | Utah | TIER ONE | T2 shell (existing Tier2RPL70Plus) | yes | 544 | 12 | 62.6 | 10.07 | 17.3 | 1.38
TIER TWO | Idaho | TIER TWO | T2 shell (existing Tier2RPL70Plus) | — | 532 | 9 | 58.7 | 9.34 | -0.4 | 0.99
TIER TWO | Kentucky | TIER THREE | T2 shell (existing Tier2RPL70Plus) | yes | 460 | 12 | 68.1 | 7.43 | 29.7 | 1.78
TIER TWO subtotal |  |  |  | 4 moving | 26333 | 435 | 65.7 |  | 5.3 | 1.09
TIER THREE | Pennsylvania | TIER TWO | T3 shell (existing Tier3RPL50Plus) | yes | 2959 | 42 | 52.3 | 8.58 | -17.3 | 0.75
TIER THREE | Indiana | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 1779 | 31 | 53 | 9.03 | -4.4 | 0.92
TIER THREE | Michigan | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 1747 | 32 | 45.8 | 8.2 | -8.8 | 0.84
TIER THREE | Oklahoma | TIER TWO | T3 shell (existing Tier3RPL50Plus) | yes | 1496 | 32 | 50.2 | 7.83 | 3.5 | 1.07
TIER THREE | Wisconsin | TIER ONE | T3 shell (existing Tier3RPL50Plus) | yes | 1349 | 25 | 54.4 | 7.75 | 0.4 | 1.01
TIER THREE | Virginia | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 1236 | 19 | 44.9 | 7.4 | -20.1 | 0.69
TIER THREE | Connecticut | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 1168 | 27 | 45.9 | 9.12 | 2.7 | 1.06
TIER THREE | Alabama | TIER ONE | T3 shell (existing Tier3RPL50Plus) | yes | 1133 | 30 | 53.6 | 6.19 | 15.8 | 1.42
TIER THREE | Maryland | TIER TWO | T3 shell (existing Tier3RPL50Plus) | yes | 951 | 19 | 46.4 | 7.2 | -3.6 | 0.93
TIER THREE | Washington | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 830 | 14 | 51.5 | 7.22 | -7.8 | 0.87
TIER THREE | Oregon | TIER ONE | T3 shell (existing Tier3RPL50Plus) | yes | 565 | 12 | 57.1 | 6.97 | 10 | 1.21
TIER THREE | Nebraska | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 509 | 9 | 55.4 | 6.53 | -1.2 | 0.98
TIER THREE | Iowa | TIER THREE | T3 shell (existing Tier3RPL50Plus) | — | 457 | 9 | 53.9 | 7.37 | 3.2 | 1.06
TIER THREE | West Virginia | (below gate) | T3 shell (existing Tier3RPL50Plus) | yes | 107 | 2 | 53 | 6.67 | -0.3 | 0.99
TIER THREE subtotal |  |  |  | 7 moving | 16285 | 303 | 50.7 |  | -3 | 0.94
TIER FOUR | New York | TIER THREE | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 1498 | 40 | 30.4 | 5.92 | -7.4 | 0.8
TIER FOUR | South Carolina | TIER THREE | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 889 | 28 | 36.1 | 5.59 | 4.4 | 1.14
TIER FOUR | Louisiana | TIER THREE | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 680 | 22 | 32.5 | 5.19 | 1.6 | 1.05
TIER FOUR | Nevada | TIER THREE | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 566 | 16 | 26.7 | 5.34 | -8.7 | 0.76
TIER FOUR | Mississippi | TIER THREE | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 334 | 9 | 17.6 | 5.05 | -19.5 | 0.47
TIER FOUR | Delaware | (below gate) | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 368 | 2 | 28.8 | 9.95 | -155.2 | 0.16
TIER FOUR | Rhode Island | (below gate) | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 198 | 6 | 20.9 | 6.59 | -12.1 | 0.63
TIER FOUR | Hawaii | (below gate) | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 121 | 5 | 19.8 | 2.96 | -4.5 | 0.82
TIER FOUR | Wyoming | (below gate) | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 60 | 2 | 29 | 7.52 | -1.1 | 0.96
TIER FOUR | South Dakota | (below gate) | zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | yes | 60 | 1 | 25.9 | 8.55 | -33.9 | 0.43
TIER FOUR subtotal |  |  |  | 10 moving | 4774 | 131 | 29.7 |  | -6.8 | 0.81

## Tier Transition Matrix
Tier transition — current (rows) vs new RPL band (columns)
Off-diagonal mass here reflects the AXIS change (margin-sorted tiers -> value-sorted bands), not an error in either map. Read it as: where each current shell's spend lands on the value axis.
Spend ($)
current ↓ / new → | TIER ONE | TIER TWO | TIER THREE | TIER FOUR | total
TIER ONE | 1806 | 3143 | 3047 | 0 | 7996
TIER TWO | 12859 | 19920 | 5405 | 0 | 38185
TIER THREE | 1343 | 3270 | 7726 | 3967 | 16306
total | 16008 | 26333 | 16179 | 3967 | 62487
State count
current ↓ / new → | TIER ONE | TIER TWO | TIER THREE | TIER FOUR | total
TIER ONE | 1 | 2 | 3 | 0 | 6
TIER TWO | 4 | 7 | 3 | 0 | 14
TIER THREE | 1 | 2 | 7 | 5 | 15
total | 6 | 11 | 13 | 5 | 35

## Shell Repurposing Map
Shell plan — what each physical campaign becomes
Assignment verified optimal on BOTH metrics: the identity mapping keeps $29.5K of $62.5K readable spend (47%) and 15 of 35 states stationary. The 20 moves are the axis change itself, irreducible by shell choice. TIER FOUR RE-ENABLES the shell retired at the July T3/T4 consolidation rather than creating a new campaign — campaign history carries into the bidder's context and the account returns to its pre-consolidation shell count. Relabel each shell at cutover (80Plus/70Plus/50Plus) that no longer match the new boundaries and would mislead reporting; campaign_id remains the stable key.
physical shell | becomes | states staying | entering | leaving (to elsewhere) | resulting spend | resulting wtd RPL | resulting wtd ROAS
T1 shell (existing Tier1RPL80Plus) | TIER ONE | 1 | 6 | 5 | 16376 | 85.5 | 1.16
T2 shell (existing Tier2RPL70Plus) | TIER TWO | 7 | 4 | 7 | 26333 | 65.7 | 1.09
T3 shell (existing Tier3RPL50Plus) | TIER THREE | 7 | 7 | 8 | 16285 | 50.7 | 0.94
zz-RETIRED-HOME INSURANCE-TIER ONE-LEGACY-NB-SEARCH-ALL-USA-STE (23428389081) | TIER FOUR | 0 | 10 | 0 | 4774 | 29.7 | 0.81

## New Tier Profile
New tier profile — value bands with current economics
RPL defines the band (grouping axis); GP/ROAS shown as the current economics each band's tROAS floor must manage. Floors on the Targets & Floors sheet.
new tier | band | states | spend | conv | wtd RPL | wtd CPL | wtd GP/lead | wtd ROAS
TIER ONE | premium value band | 7 | 16376 | 221 | 85.5 | 74 | 11.6 | 1.16
TIER TWO | upper-mid value band | 11 | 26333 | 435 | 65.7 | 60.5 | 5.3 | 1.09
TIER THREE | mid value band | 14 | 16285 | 303 | 50.7 | 53.7 | -3 | 0.94
TIER FOUR | low value band | 10 | 4774 | 131 | 29.7 | 36.5 | -6.8 | 0.81

## Targets & Floors
tROAS floors — margin policy pending (editable)
Floor = 1/(1 - margin). Enter leadership's chosen margin per band in the blue cells; floor, max CPL and gap-to-current recompute live. Floors are MINIMUM targets. LAUNCH each shell at ~its current effective target, then STEP toward the floor 15-20% per adjustment, >=1 week between steps — target moves are phased even though membership is not.
new tier | wtd RPL | margin % (EDIT) | tROAS floor | implied max CPL | current realized ROAS | gap to floor | step plan
TIER ONE | 85.5 | 20% | 125% | 68.4 | 1.16 | -0.09 | launch at current effective target; step 15-20% toward floor, >=1wk apart
TIER TWO | 65.7 | 12% | 113.6% | 57.816 | 1.09 | -0.046364 | launch at current effective target; step 15-20% toward floor, >=1wk apart
TIER THREE | 50.7 | 5% | 105.3% | 48.165 | 0.94 | -0.11263 | launch at current effective target; step 15-20% toward floor, >=1wk apart
TIER FOUR | 29.7 | 0% | 100% | 29.7 | 0.81 | -0.19 | launch at current effective target; step 15-20% toward floor, >=1wk apart

## Exception Watch
Exception screen — day-one watch list
The RPL bands sort VALUE; the biweekly GP exception screen handles POSTURE. These states enter the new structure already flagged (evidence from the instrumented July reads). Screen is watch-only during the 2-week post-cutover freeze.
state | lands in | flag | evidence (July reads) | likely disposition | review
Massachusetts | TIER ONE | negative margin entering premium band | persistent negative GP/lead at high RPL; expensive clicks | per-state target exception or rehab if floor unmet | cycle 1
Pennsylvania | TIER THREE | pre-cutover exception (executed) | -$50/lead recent, 88% bootstrap, deteriorating | per-state target exception or rehab if floor unmet | cycle 1
Arizona | TIER TWO | pre-cutover exception (executed) | persistent negative margin; value recovered, cost did not | per-state target exception or rehab if floor unmet | cycle 1
Alabama | TIER THREE | strong earner in low band | ~1.3-1.4 ROAS at modest RPL | upward posture exception once floors live | cycle 1-2
Wisconsin | TIER THREE | strong earner in low band | recovered to ~1.2-1.4 ROAS (July reads) | upward posture exception once floors live | cycle 1-2
Georgia | TIER TWO | largest spend at ~breakeven, slipping | 0.90-1.03 ROAS on top tiered spend | repair-in-place (query/device surgery), not a tier move | ongoing

## Risks & Sequencing
Risks, sequencing & controls
Single cutover, by design
20 of 35 readable states change shells — a majority-move restructure. Phasing a majority-move map means weeks of mixed-regime shells and staggered learning resets (the June rollout demonstrated this: three staggered resets, contaminated measurement). One synchronized event = one turbulence window, one clean before/after.
Bidder learning reset
All shells reset at cutover (~1-2 weeks). FREEZE: no target changes and exception screen watch-only for 2 weeks post-cutover. Do not grade the structure on the freeze window.
Targets phase, membership doesn't
Launch each shell near its current effective aggressiveness; step toward the policy floors 15-20% per adjustment, >=1 week apart. Large single target jumps caused the May-June overcorrection.
Ledger frozen at cutover
Run the model with --emit-ledger on cutover day against the final as-built export. The new structure starts with a commitment ledger from day one; all future runs compare against it.
Relabel + id stability
Relabel each shell at cutover. campaign_id is the analysis key; update any name-parsing logic the same day.
Fresh location export first
Iron rule: pull a fresh campaign-location export immediately before building the change set; audit for dual-targeting and orphaned states.
Re-enabled shell hygiene
The retired shell is re-enabled with its OLD contents intact: audit and reset before cutover — location targets (strip all old states), keywords/negatives (align to current library), budget, and especially its old tROAS setting (it will resume at its retirement-era target unless changed). A paused campaign may not appear in an enabled-only location export — pull it explicitly and confirm its campaign_id for the change set.
Below-gate states
Thin states placed by nearest-tier (shrunk where available) and folded in at cutover — no separate wave. They carry no launch-target weight.
Don't stack levers
No keyword/geo/budget surgery on tiered shells within the freeze window.